## Sheet1
Tasks by Team Member: Alex Tonkin |  |  | Tasks by Team Member: Ashwin D'Cruz |  |  | Tasks by Team Member: Cameron Johnson
Task Name | Duration (hrs) | Responsible | Task Name | Duration (hrs) | Responsible | Task Name | Duration (hrs) | Responsible
Phase 1 - Planning and Research |  |  | Phase 1 - Planning and Research |  |  | Phase 2 - Skeleton Implementation
Analyze input data format | 4 | Alex | Write out initial documentation | 5 | Ashwin | Analyze output data format | 4 | Cameron
Phase 2 - Skeleton Implementation |  |  | Phase 2 - Skeleton Implementation |  |  | Write code to write .vid files | 4 | Cameron
Write code to read .csv files | 4 | Alex | Write out function stubs | 5 | Ashwin | Deliverable A
Deliverable A |  |  | Deliverable A |  |  | Write draft 1 | 1 | ALL
Write draft 1 | 1 | ALL | Write draft 1 | 2 | ALL | Collect client feedback | 2 | ALL
Collect client feedback | 2 | ALL | Collect client feedback | 2 | ALL | Revise document | 1 | ALL
Revise document | 1 | ALL | Revise document | 2 | ALL | Phase 3 - Algorithm Logic
Phase 3 - Algorithm Logic |  |  | Phase 3 - Algorithm Logic |  |  | Write player load heuristic | 10 | Cameron, Kieran
Write GPS heuristic | 10 | Alex, Kieran | Write code to handle grounds | 10 | Dean, Ashwin, Marcus | Deliverable B
Deliverable B |  |  | Deliverable B |  |  | Collect client input | 2 | ALL
Collect client input | 2 | ALL | Collect client input | 2 | ALL | Phase 4 - Enhancements
Phase 4 - Enhancements |  |  | Create Acceptance tests | 2 | Marcus, Ashwin | Optimise algorithms | 10 | Alex, Cameron
Optimise algorithms | 10 | Alex, Cameron | Phase 4 - Enhancements |  |  | Other additions | 5 | ALL
Other additions | 5 | ALL | Other additions | 5 | ALL | Deliverable C
Deliverable C |  |  | Deliverable C |  |  | Clean GitHub issues log and obtain print | 3 | Cameron
Prepare code printouts | 3 | Alex | Conduct test suite, obtain results | 5 | Ashwin | Deliverable D
Deliverable D |  |  | Deliverable D |  |  | Prepare presentation | 3 | ALL
Prepare presentation | 3 | ALL | Prepare presentation | 5 | ALL | Group Meetings | 15 | ALL
Group Meetings | 15 | ALL | Group Meetings | 15 | ALL | Total: | 60
Total: | 60 |  | Total: | 60
Tasks by Team Member: Dean Cook |  |  | Tasks by Team Member: Marcus Pham |  |  | Tasks by Team Member: Kieran Hannigan
Task Name | Duration (hrs) | Responsible | Task Name | Duration (hrs) | Responsible | Task Name | Duration (hrs) | Responsible
Phase 1 - Planning and Research |  |  | Phase 1 - Planning and Research |  |  | Phase 1 - Planning and Research
Research Junit | 3 | Dean | Research GUI frameworks |  |  | Create UML class diagram | 1 | Kieran
Research GUI frameworks |  |  | Research Swing | 3 | Marcus | Sketch draft GUI | 1 | Kieran
Research JavaFX | 3 | Dean | Research QT | 3 | Marcus | Phase 2 - Skeleton Implementation
Research other GUI possibilities | 3 | Dean | Deliverable A |  |  | Create folder structure | 0.5 | Kieran
Deliverable A |  |  | Write draft 1 | 5 | ALL | Create code files | 0.5 | Kieran
Write draft 1 | 1 | ALL | Collect client feedback | 3 | ALL | Implement GUI | 15 | Kieran
Collect client feedback | 2 | ALL | Revise document | 5 | ALL | Attach UI elements to functionality | 3 | Kieran
Revise document | 1 | ALL | Phase 3 - Algorithm Logic |  |  | Deliverable A
Phase 3 - Algorithm Logic |  |  | Write code to handle grounds | 5 | Dean, Ashwin, Marcus | Collect client feedback | 2 | ALL
Write code to handle grounds | 10 | Dean, Ashwin, Marcus | Deliverable B |  |  | Revise document | 2 | ALL
Deliverable B |  |  | Collect client input | 3 | ALL | Phase 3 - Algorithm Logic
Collect client input | 2 | ALL | Create Acceptance tests | 3 | Marcus, Ashwin | Write (help with) GPS heuristic | 1 | Alex, Kieran
Create project model diagrams | 15 | Dean | Phase 4 - Enhancements |  |  | Write (help with) player load heuristic | 1 | Cameron, Kieran
Phase 4 - Enhancements |  |  | Other additions | 5 | ALL | Write algorithm balancer | 5 | Kieran
Other additions | 5 | ALL | Deliverable C |  |  | Deliverable B
Deliverable C |  |  | Write up instruction document | 5 | Marcus | Collect client input | 2 | ALL
Prepare time analysis and discussion | 5 | Dean | Deliverable D |  |  | Create Project Plan documents | 3 | Kieran
Deliverable D |  |  | Prepare presentation | 5 | ALL | Phase 4 - Enhancements
Prepare presentation | 10 | ALL | Group Meetings | 15 | ALL | Refactor Grounds UI | 3 | Kieran
Total: | 60 |  | Total: | 60 |  | Deliverable C
[6 empty] | Clean git log and obtain branch print | 1 | Kieran
[6 empty] | Prepare ethics analysis and dicsussion | 3 | Kieran
Deliverable D
[6 empty] | Prepare presentation | 1 | ALL
[6 empty] | Group Meetings | 15 | ALL
[6 empty] | Project Management Bookkeeping | 10 | Kieran
[6 empty] | Total: | 70