## Sheet1
Task # | Task Name | Duration | Start | Finish | Requires | Responsible
1 | Phase 1 - Planning and Research | 7 days | Sun 14-08-03 | Sat 14-08-09
2 | Create UML class diagram | 2 days | Sun 14-08-03 | Mon 14-08-04 |  | Kieran
3 | Write out initial documentation | 2 days | Tue 14-08-05 | Wed 14-08-06 | 2 | Ash
4 | Analyze input data format | 2 days | Sun 14-08-03 | Mon 14-08-04 |  | Alex
5 | Analyze output data format | 2 days | Sun 14-08-03 | Mon 14-08-04 |  | Cameron
6 | Research Junit | 1 day | Sun 14-08-03 | Sun 14-08-03 |  | Dean
7 | Research GUI frameworks | 2 days | Sun 14-08-03 | Mon 14-08-04
8 | Research Swing | 1 day | Sun 14-08-03 | Sun 14-08-03 |  | Marcus
9 | Research QT | 1 day | Mon 14-08-04 | Mon 14-08-04 | 8 | Marcus
10 | Research JavaFX | 1 day | Sun 14-08-03 | Sun 14-08-03 |  | Dean
11 | Research other GUI possibilities | 1 day | Mon 14-08-04 | Mon 14-08-04 | 10 | Dean
12 | Sketch draft GUI | 1 day | Tue 14-08-05 | Tue 14-08-05 | 7 | Kieran
13 | Phase 2 - Skeleton Implementation | 16 days | Sun 14-08-10 | Mon 14-08-25 | 1
14 | Create folder structure | 0.5 days | Sun 14-08-10 | Sun 14-08-10 |  | Kieran
15 | Create code files | 0.5 days | Sun 14-08-10 | Sun 14-08-10 | 14 | Kieran
16 | Write out function stubs | 2 days | Mon 14-08-11 | Tue 14-08-12 | 15 | Ashwin
17 | Write code to read .csv files | 4 days | Wed 14-08-13 | Sat 14-08-16 | 16 | Alex
18 | Write code to write .vid files | 4 days | Wed 14-08-13 | Sat 14-08-16 | 16 | Cameron
19 | Implement GUI | 7 days | Wed 14-08-13 | Tue 14-08-19 | 16 | Kieran
20 | Attach UI elements to functionality | 3 days | Sat 14-08-23 | Mon 14-08-25 | 21 | Kieran
21 | Deliverable A | 3 days | Wed 14-08-20 | Fri 14-08-22
22 | Write draft 1 | 1 day | Wed 14-08-20 | Wed 14-08-20 |  | ALL
23 | Collect client feedback | 1 day | Thu 14-08-21 | Thu 14-08-21 | 22 | ALL
24 | Revise document | 1 day | Fri 14-08-22 | Fri 14-08-22 | 23 | ALL
25 | Phase 3 - Algorithm Logic | 14 days | Thu 14-09-04 | Wed 14-09-17 | 13,30
26 | Write GPS heuristic | 14 days | Thu 14-09-04 | Wed 14-09-17 |  | Alex, Kieran
27 | Write player load heuristic | 14 days | Thu 14-09-04 | Wed 14-09-17 |  | Cameron, Kieran
28 | Write algorithm balancer | 7 days | Thu 14-09-04 | Wed 14-09-10 |  | Kieran
29 | Write code to handle grounds | 1 day? | Thu 14-09-04 | Thu 14-09-04 |  | Dean, Ashwin, Marcus
30 | Deliverable B | 3 days | Mon 14-09-01 | Wed 14-09-03 | 22
31 | Collect client input | 1 day | Mon 14-09-01 | Mon 14-09-01 |  | ALL
32 | Create Project Plan documents | 2 days | Tue 14-09-02 | Wed 14-09-03 | 31 | Kieran
33 | Create Use Case diagram | 2 days | Tue 14-09-02 | Wed 14-09-03 | 31 | Dean
34 | Create Acceptance tests | 2 days | Tue 14-09-02 | Wed 14-09-03 | 31 | Marcus, Ashwin
35 | Phase 4 - Enhancements | 7 days | Sun 14-09-21 | Sat 14-09-27 | 25
36 | Optimise algorithms | 7 days | Sun 14-09-21 | Sat 14-09-27 |  | Alex, Cameron
37 | Refactor Grounds UI | 7 days | Sun 14-09-21 | Sat 14-09-27 |  | Kieran
38 | Other additions | 7 days | Sun 14-09-21 | Sat 14-09-27 |  | ALL
39 | Deliverable C | 5 days | Sun 14-10-12 | Thu 14-10-16 | 35
40 | Prepare code printouts | 3 days | Sun 14-10-12 | Tue 14-10-14 |  | Alex
41 | Write up instruction document | 3 days | Sun 14-10-12 | Tue 14-10-14 |  | Marcus
42 | Clean git log and obtain branch print | 3 days | Sun 14-10-12 | Tue 14-10-14 |  | Kieran
43 | Clean GitHub issues log and obtain print | 3 days | Sun 14-10-12 | Tue 14-10-14 |  | Cameron
44 | Conduct test suite, obtain results | 3 days | Sun 14-10-12 | Tue 14-10-14 |  | Ashwin
45 | Prepare time analysis and discussion | 5 days | Sun 14-10-12 | Thu 14-10-16 |  | Dean
46 | Prepare ethics analysis and dicsussion | 5 days | Sun 14-10-12 | Thu 14-10-16 |  | Kieran
47 | Deliverable D | 7 days | Sun 14-10-19 | Sat 14-10-25 | 39
48 | Prepare presentation | 7 days | Sun 14-10-19 | Sat 14-10-25 |  | ALL